## Лист1
Task title | Task description | Estimates | Status | Progress
Identifiers declaration | Parse source code into the tree-like structure of scopes and identifiers | 1mw | Completed | 100%
Comments removing | Remove line and block comments from source code | 5mh | Completed | 100%
Tokens parsing | Convert source code (scope-identifiers structure) into the tokens | 2mw | Analysis | 0%
Projects naming | Analyze and improve projects and namespaces naming | 2md | Analysis | 0%
Native testing improvements | Analyze Visual Studio features for test-cases | 1mm | In Queue | 0%